PREP SCHEDULE FOR FILM & TV PRODUCTION

Prep schedules for film and television production vary with the nature of the productions themselves.  This document will outline the various meetings required during the preparation of a one-hour episode.  Because of the nature of series production - that is one episode preps while the previous episode is shooting - the prep period is very compressed, seven to eight working days.   For a single project these meetings might be spread over weeks or even months.

Comments below are in italics.

Title of Production

Name of Production Company

Name and contact info for key production contact* – phone number and email

* Producer, Production Manager, 1st A.D.

Prep Schedule as of date of issue

Subsequent changes, like scripts, are printed in coloured paper and changes are marked with an asterisk.

Date & Time column 		Name of Meeting		Who is required to attend

Day One		Concept Meeting			Producer, Director, Writer, 									DoP, Camera Operator, 									Gaffer, P.M., 1st and 2nd 									A.D.s, Design keys, 										including Locations and 									VFX, Post Supervisor, 									Editors

Producer and director describe their overall vision for the film.  The attendees have been expanded to reflect a single, one-off production.  First A.D. goes through script, special needs are flagged for each department, questions addressed by producer, director, writer.  This also functions as the overall design meeting.

Location Meeting #1			As above

Preliminary show and tell, photos of potential locations reviewed.

Day Two		Location Scout			Producer, Director, Writer, 									Production Designer, 1st 									A.D., Locations

Day Three		Casting				Producer, Director, Writer, 									Casting Director, Reader, 									Video Operator

Day Four		Costume Meeting			Producer, Director, Writer, 									Production Designer, 1st  & 									2nd A.D., Costume Designer, 									Assistant Costume Designer

Hair/Makeup Meeting			Producer, Director, 										Writer,  Production 										Designer, 1st & 2nd 										A.D., Key Hair and 										Key Makeup

Background Meeting			Producer, Director, 										Writer,  1st & 2nd 										A.D., Extras Casting,  									Production Designer										Costume Designer, Costume 									Assistant, Key Hair and 									Key Makeup as required

Days Five, Six		Locations and Set Review with DoP		Producer, Director, 										Production Designer, 										DoP, Gaffer, Key 										Grip, Location 										Sound Recordist, 1st 										& 2nd A.D.

Ideally this is done on the locations but that may not be practical and sets may not be ready, so photos and floor plans may have to suffice.

Props, Set Dec, SFX meeting		Producer, Director, 										Writer, Production 										Designer, 1st & 2nd 										A.D., Key Props, Key Set 									Dec., SFX

Key props and special effects should be demonstrated at this meeting and approved.  All SFX should be demonstrated prior to the day they are required for principal photography.  If they don’t work, a new date and time for a second demonstration should be scheduled.  Do not expect a special effect to work on set if you have not seen it demonstrated beforehand.

Graphics and Still Photos		Producer, Director, 										Writer, Production 										Designer, 1st & 2nd 										A.D., Graphic Artist, Still 									Photographer

Since on a student film, the photographer doing stills to be featured on camera will probably also be the unit photographer, this meeting could also cover unit photography.

Days Five, Six		Additional Meetings as required –	Producer, Director, 					VFX, Wranglers, Transportation 	Writer, Production 					(picture vehicles), Video and/or	Designer, 1st & 2nd

Audio playback, Design stages	A.D.s

Day Six		Post Production Meeting 		Producer, Director, 										Writer, Production 										Designer, 1st & 2nd 										A.D., Graphic Artist, Still 									Photographer, Post 										Supervisor, Picture Editor, 									Sound Editor, VFX Artist, 									Composer, Music Supervisor

Post production concepts, preliminary VFX, production needs for post, schedules.

Day Seven		Tech Survey				Producer, Director, Writer, 									P.M., 1st and 2nd A.D.s 									All Design keys, including 									Locations, all Production 									keys.

Director explains at each location and on each set, how each scene will be shot, what he or she will require.  Answers questions.

Timeline Meeting			Director and 1st A.D.

Director and First estimate how long it will take to shoot each scene, based on schedule.

Cast Read Through			Producer, Director, Writer, 									P.M., 1st and 2nd A.D.s, 									Principal Cast, Continuity

Day Eight		Production Meeting			Producer, Director, Writer, 									P.M., 1st and 2nd A.D.s 									All Design keys, including 									Locations, all Production 									keys, Post Supervisor and 									Editors.

First A.D. reviews the schedule and the script, scene by scene, highlights important issues, questions asked and answered.

Tone Meeting				Producer, Director, Writer

A final review of the script and shooting plan, focusing on performance, important beats of the story, theme, how these will be reflected/captured in composition and montage.

David Barlow

3-16-12